## Slide 1
Software Project Management
Lessons from the Field
Mark Kimmey
11 November 2014

## Slide 2
Credentials
USMA 1982
  General Engineering, Electrical Engineering and Computer Science
Army experience
  New uses for old technology
  First “PC” on a commander’s desk
  Logistics Management College
Defense Contracting (I & II)
  Software development – testing and manuals
  Project management
Warehouse Automation
  Boxes of moo and Bugs Bunny dolls
AEC
  Collaboration spaces (eRoom, SharePoint) and project management systems for large engineering efforts
2
Notes: 2

## Slide 3
Clichés
We learn more from bad decisions than from good ones.
Bad decisions result from a lack of experience. Experience is the result of making bad decisions.
It is better to learn from the mistakes of others than from our own.
3
Notes: 3

## Slide 4
Hot Topics
Earned Value Analysis
Domain-Analysis-Driven WBS Construction
  enterprise standards and the risks
  requirements document approach
  course of action analysis – “war gaming”
Basic Scheduling in Microsoft Project
  working around the limitations
    hours per day, predecessors
  curb your enthusiasm – and ambition
Managerial Politics
  advantages of a schedule
Leadership
  who’s important?
4
Notes: 4

## Slide 5
Hot Topics
Software Process Automation
  the debate over waterfall vice Agile/Scrum
PMI Certification
5
Notes: 5

## Slide 6
An Unfortunate Question
How many of you think you’re going to work for a software company where you get to sit around being creative?
Wanna’ bet?
6
Notes: 6

## Slide 7
The Rules
Integrity is non-negotiable.
Bad news does not get better with time.
Don’t make rules you’re not willing to enforce.
Don’t assume, “someone knows about that.”
If you don’t know, ask.
Hope is not a method.
Document everything.
Do your homework.
Deliver.
7
Notes: 7

## Slide 8
Great Truths
You only get one chance to be trusted: don’t tap-dance.
If you screw up, admit it and ask for help quickly.
Unenforced rules teach employees that you aren’t serious about discipline, deadlines or quality. Guess what happens?
Project Managers need to make sure that everyone knows what everyone else is doing.
If you don’t know, ask. There is such a thing as a stupid question, but ask anyway: the guy next to you might be wondering the same thing.
Hope is not a method. Neither is prayer. See #2.
8
Notes: 8

## Slide 9
Great Truths
7. Document everything. Whoever owns the notes, owns the project.
8. Do your homework: there is always a sharpshooter. There is always someone who wants to use your meeting or presentation to prove how smart they are.
It doesn’t make any difference how great a person you are if you can’t come though when your boss/client needs something.
9
Notes: 9

## Slide 10
Things Nobody Tells You
Communication is key – collaboration and project management tools can help, but…
Clients do not read contracts
Billability Rules
Reports are reality – and will be used against you; the risks of dashboards
The budget isn’t what you think it is
The reports are late, and they’re wrong
Project Managers should be part of the proposal team
10
Notes: 10

## Slide 11
Things Nobody Tells You
You are not funny
Written communications must be tight – email, presentations, anything: no “texting,” and spelling counts
Tuck in your shirt
11
Notes: 11

## Slide 12
Period of Performance: 9 July 2013 – 8 July 2016
Labor Expenses Total
Budget (does not include fee): $6,636. $17,843. $24,480.
Funded (does not include fee): $6,636. $17,843 $24,480.
Expended (does not include fee): $3,997. $10,018. $14,015.
% Complete (schedule): 58.9% 58.9% 58.9%
% Complete (funding) 60.23% 56.14% 57.25%
Estimate to Complete (schedule) (current funding): 8 August 2015
Estimate to Complete (funding): $9,235.
Over/Under Plan (schedule): On schedule
Over/Under Plan (funding): $1,230. (under)
Project Status – xxxxxx (hosting)
12
Notes: 12

## Slide 13
Project Status – xxxxxx (hosting)
13
Chart: Overall Status - Web Hosting Services
| 41456 | 41487 | 41518 | 41548 | 41579 | 41609 | 41640 | 41671 | 41699 | 41730 | 41760 | 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522
Funding | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136 | 24479.8136
80% Funding | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509 | 19583.8509
Expended | 2260.5119 | 3036.9919 | 3763.4719 | 4624.2719 | 5425.7519 | 6202.2319 | 7080.1519 | 7881.6319 | 8658.1119 | 9536.0319 | 10363.9519 | 11316.8719 | 12405.5919 | 13311.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919 | 14014.5919
Estimate | 2260.51 | 3036.99 | 3763.47 | 4624.27 | 5425.75 | 6202.23 | 7080.15 | 7881.63 | 8658.11 | 9536.03 | 10363.95 | 11316.87 | 12405.59 | 13311.59 | 14014.59 | 14854.1671 | 15693.7443 | 16533.3214 | 17372.8986 | 18212.4757 | 19052.0529 | 19891.63 | 20731.2071 | 21570.7843 | 22410.3614 | 23249.9386 | 24089.5157 | 24929.0929 | 25768.67 | 26608.2471 | 27447.8243 | 28287.4014 | 29126.9786 | 29966.5557 | 30806.1329 | 31645.71
Plan | 4408.33 | 6325.21 | 8242.09 | 10158.97 | 12075.85 | 13992.73 | 15909.61 | 17826.49 | 19743.37 | 21660.25 | 23577.13 | 25494.01 | 27410.89 | 29327.77 | 31244.65 | 33161.53 | 35078.41 | 36995.29 | 38912.17 | 40829.05 | 42745.93 | 44662.81 | 46579.69 | 48496.57 | 50413.45 | 52330.33 | 54247.21 | 56164.09 | 58080.97 | 59997.85 | 61914.73 | 63831.61 | 65748.49 | 67665.37 | 69582.25 | 71499.13
Notes: 13

## Slide 14
Project Status – xxxxxx (hosting)
14
Chart: Labor - Web Hosting Services
| 41456 | 41487 | 41518 | 41548 | 41579 | 41609 | 41640 | 41671 | 41699 | 41730 | 41760 | 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522
Funding | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636 | 6636.3636
80% Funding | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909 | 5309.0909
Expended | 2167.77 | 2244.25 | 2320.73 | 2506.53 | 2583.01 | 2659.49 | 2812.41 | 2888.89 | 2965.37 | 3118.29 | 3271.21 | 3424.13 | 3762.85 | 3918.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85 | 3996.85
Estimate | 2167.77 | 2244.25 | 2320.73 | 2506.53 | 2583.01 | 2659.49 | 2812.41 | 2888.89 | 2965.37 | 3118.29 | 3271.21 | 3424.13 | 3762.85 | 3918.85 | 3996.85 | 4127.4986 | 4258.1471 | 4388.7957 | 4519.4443 | 4650.0929 | 4780.7414 | 4911.39 | 5042.0386 | 5172.6871 | 5303.3357 | 5433.9843 | 5564.6329 | 5695.2814 | 5825.93 | 5956.5786 | 6087.2271 | 6217.8757 | 6348.5243 | 6479.1729 | 6609.8214 | 6740.47
Plan | 3158.33 | 3825.21 | 4492.09 | 5158.97 | 5825.85 | 6492.73 | 7159.61 | 7826.49 | 8493.37 | 9160.25 | 9827.13 | 10494.01 | 11160.89 | 11827.77 | 12494.65 | 13161.53 | 13828.41 | 14495.29 | 15162.17 | 15829.05 | 16495.93 | 17162.81 | 17829.69 | 18496.57 | 19163.45 | 19830.33 | 20497.21 | 21164.09 | 21830.97 | 22497.85 | 23164.73 | 23831.61 | 24498.49 | 25165.37 | 25832.25 | 26499.13
Notes: 14

## Slide 15
Project Status – xxxxxx (hosting)
15
Chart: Direct Costs - Web Hosting Services
| 41456 | 41487 | 41518 | 41548 | 41579 | 41609 | 41640 | 41671 | 41699 | 41730 | 41760 | 41791 | 41821 | 41852 | 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522
Funding | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45 | 17843.45
80% Funding | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76 | 14274.76
Expended | 92.7419 | 792.7419 | 1442.7419 | 2117.7419 | 2842.7419 | 3542.7419 | 4267.7419 | 4992.7419 | 5692.7419 | 6417.7419 | 7092.7419 | 7892.7419 | 8642.7419 | 9392.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419 | 10017.7419
Estimate | 92.74 | 792.74 | 1442.74 | 2117.74 | 2842.74 | 3542.74 | 4267.74 | 4992.74 | 5692.74 | 6417.74 | 7092.74 | 7892.74 | 8642.74 | 9392.74 | 10017.74 | 10726.6686 | 11435.5971 | 12144.5257 | 12853.4543 | 13562.3829 | 14271.3114 | 14980.24 | 15689.1686 | 16398.0971 | 17107.0257 | 17815.9543 | 18524.8829 | 19233.8114 | 19942.74 | 20651.6686 | 21360.5971 | 22069.5257 | 22778.4543 | 23487.3829 | 24196.3114 | 24905.24
Plan | 1250 | 2500 | 3750 | 5000 | 6250 | 7500 | 8750 | 10000 | 11250 | 12500 | 13750 | 15000 | 16250 | 17500 | 18750 | 20000 | 21250 | 22500 | 23750 | 25000 | 26250 | 27500 | 28750 | 30000 | 31250 | 32500 | 33750 | 35000 | 36250 | 37500 | 38750 | 40000 | 41250 | 42500 | 43750 | 45000
Notes: 15

## Slide 16
≥ 42 days ≥ 70 days
Aged Receivables: none none
Unbilled Costs (w/out fee): $2,468.32
Project Status – (hosting) – Invoicing
16
Notes: 16

## Slide 17
none
Project Status – xxxxxx (hosting) – MODs
17
Notes: 17

## Slide 18
Project Status – xxxxxx (hosting) – Issues
In order to maximize the funded period of performance, we have examined burn rates and reallocated funds between labor and direct costs. Expenditure of current funds is expected to occur in August 2015.
18
Notes: 18

## Slide 19
Kimmey’s Humble Opinion – that thing called “data”
Data what is it?
Information what does it mean? (processed data)
Knowledge is it important? (interpreted information)
Insight what can I do with it? (the fuzzy area)
19
Notes: 19

## Slide 20
Kimmey’s Humble Opinion – the credit card statement
Data individual transactions
Information statements/reports, totals, balances, fees paid, credit remaining, total interest paid
Knowledge spending rate, payment track record, how long to pay off, impact on future spending
Insight spending habits, alternatives
20
Notes: 20

## Slide 21
Kimmey’s Humble Opinion – the late night drive
Data gas gauge
Information miles to empty
Knowledge miles to empty vice miles to destination
Insight decision on if/where/when to refuel
21
Notes: 21