## Slide 1: Microsoft Project 2010 – Introduction, Part 4
Phil Pfeiffer
Fall, 2014

## Slide 2: This Presentation's Structure
Part 1
  Common features & their uses
    Gantt Chart View
    Tasks
    Scheduling Modes: Manual Mode
    Inter-Task Dependencies
    Resources
    Other operations on tasks
Part 2
  Common features, uses (cont.)
    Overallocation
    Duration, Units, Work
    Scheduling Modes: Auto Scheduling
    Scheduling Modes: Recommendations
Part 3
  Common features, uses (cont.)
    Summary tasks and subtasks
    Summary Tasks: Auto Scheduling
    Summary Tasks: Inter-Task Dependencies
    Calendars
    Calendar Management
Part 4
  Common features, uses (cont.)
    Calendar Management (cont.)
    Modifying Calendars
    Skewed Calendars
    Calendar Architectures
    Project Tracking
  Key limitations and gotchas

## Slide 3: Calendar Management (Project)
The project shown here pairs
  task 1 with no calendar and
  person 1 and the project as a whole with Standard
Standard has been modified, using the Change Working Time / Exceptions tab, to treat Bastille Day (14 July 2014) as a full holiday.
  Note that treating 14 July 2014 as a holiday causes Project to shift the schedule from 14-15 July to 15-16 July.

## Slide 4: Calendar Management (Project)
Closeups of the Change Working Time / Exceptions and Details menus. The Details menu was opened by clicking on the Change Working Time menu's Details… control.

## Slide 5: Calendar Management (Project)
The project shown here pairs
  task 1 with no calendar and
  person 1 and the project as a whole with Standard
Standard has been modified, using the Change Working Time / Exceptions tab, to treat Bastille Day (14 July 2014) as a half-day holiday; employees have the afternoon off
  Note that treating 14 July 2014 as a half-day holiday causes Project to shift the schedule from 14-15 July to 14 July 8 am – 16 July noon.

## Slide 6: Calendar Management (Project)
Closeups of the Change Working Time / Exceptions and Details menus. The Details menu was opened by clicking on the Change Working Time menu's Details… control.

## Slide 7: Calendar Management (Project)
The project shown here pairs
  task 1 with no calendar and
  person 1 and the project as a whole with Standard
Standard has been modified, using the Change Working Time / Work Weeks tab, to treat the default work week as a half-day week; employees have every afternon off
  Note that treating work days as half-day holidays causes Project to shift the schedule from 14-15 July to 14-17 July: i.e., 4 hours per day * 4 days = 16 hours

## Slide 8: Calendar Management (Project)
Closeups of the Change Working Time / Work Weeks and Details menus. The Work Weeks menu was opened by clicking on the Change Working Time menu's Details… control.

## Slide 9: Modifying Calendars: Guidelines
Managing the default work week
  The default work week's start and end fields (N/A) can't be changed.
  The default work week hours can be changed.
    This typically means reducing them: e.g., to 8-11 am and 1-4 pm to account for non-productive overhead in a typical work week
    If you need to expand them, Project help guides recommend switching to the 24 hour schedule instead
Managing non-default work weeks
  Work week table entries are spans of days - 1000 max for any one entry
  A span of days can most easily be specified by
    Selecting the span from the calendar above the table
    Then entering a name for the block in the Name column
  Non-default time frames in the tables can't overlap.
    Project 2010 gets quite fussy about this; it won't deselect a work week that overlaps with another work week until you change spans
Managing exceptions
  Entries in the exceptions table supersede those in the work week table
  Use exceptions for special "events" like holidays and training

## Slide 10: Scheduling with Multiple Resources
Review
Adding a second work resource for a fixed units, non-effort-driven task doubles the work without changing the duration
Selecting the information pop-up option for reduced duration then has the effect of halving the schedule, while keeping work constant

## Slide 11: Resource Calendars
Every resource, when first created, gets its own calendar
This calendar can be accessed with the For calendar: dropdown, located in the menu obtained by clicking the Project tab's Change Working Time icon
This calendar
  Has the same name as its resource
  Inherits its properties from the project calendar in force at the time

## Slide 12: Skewed Resource Calendars
Resource-specific calendars allow working times to be tailored to individual resources
Here, for example, person 2's default work week is set to afternoons only.
The change produces a schedule with a 12-hour duration

## Slide 13: Skewed Resource Calendars
The resource usage and task usage views clarify Project's calculated schedule.
Project assigns the extra work to person 2 rather than person 1, which extends the schedule by 5 hours in real time: i.e.,
if person 1 had been assigned the leftover work after 7/14, the task would have been finished by noon rather than 5 pm.
Project appears to calculate duration from the times when either person 1 or person 2 works on the task. Note that Tuesday am doesn't enter into the duration.

## Slide 14: Skewed Resource Calendars
Requesting Fixed Effort scheduling for the Fixed-Units-Scheduled task 1 fails to shift work to person 1. Ditto for requesting Fixed Work scheduling for this task.
A tighter schedule can be obtained by hand-editing Project's schedule. Here, the 15 July allocation of 4h person 2 was deleted and replaced by a 4h, 8am allocation to person 1.
Project flags both resources' schedules as hand edited in the Resource Usage view's information column.

## Slide 15: Skewed Resource Calendars
As a rule, I strongly recommend using Project's automated leveling feature instead of doing leveling by hand
  Auto leveling is far less error prone
  Auto leveling is also far less tedious – particularly for larger, more complex schedules
In this case, however, I can't figure out how to get auto leveling to tighten this schedule
  And, for what it's worth, I've seen relatively little detailed documentation on Microsoft's scheduling and leveling algorithms, which I'm guessing are proprietary.

## Slide 16: Skewed Resource Calendars, Different Bases
This series of examples starts with a two-person, 2-day-long task.
Initially, persons 1 and 2 are scheduled according to Project's Standard schedule.
If person 2's base schedule is changed to Night Shift to expedite the project …
….Nothing changes.

## Slide 17: Skewed Resource Calendars, Same Bases
Another strategy for accelerating the schedule sets person 2's
Base calendar to Standard and
Working hours for 14-18 to 8 am to 12 am (i.e., midnight)

## Slide 18: Skewed Resource Calendars, Same Bases
This attempt at schedule adjustment works well, at first glance
  person 2 is now scheduled to work from 5 pm until 12 midnight
  person 1 now picks up the 8 leftover hours on 15 July
Splitting the work on 15 July would accelerate termination by 4 hours
However, I can't get Project to level in increments of less than 1 day
  … even though the leveling options for
    adjusting individual assignments in tasks and
    creating splits in remaining work
  are enabled by default (see Resource / Leveling Options control)
Worse, this strategy breaks down in the presence of summary tasks

## Slide 19: Skewed Resource Calendars, Same Bases
Making task 1 a subtask of a summary task subjects task 1 to the summary task's schedule, causing Project to ignore person 2's 5 pm – midnight work schedule
This is because summary 1, when created, inherited the project's main schedule
… and the project's main schedule, Standard, excludes evening hours

## Slide 20: Working with Multiple Calendars: Advice
Adapt your use of calendars to Project's limitations: i.e., for every project,
  Define one main calendar
  Assure that the main calendar's hours encompass all possible working times
      If any project work can be scheduled for a given day at a given time, that day and time should be treated as work time in the main calendar
  Assure that every work resource uses this main calendar as its base calendar
Benefits: this strategy
  allows Project's leveling algorithm to work effectively, but
  limits a project plan to a two-level architecture for calendar representation
Problems: this strategy
  makes it impossible to frame "mid-level" scheduling policies for projects with different groups of workers who work different sets of hours

## Slide 21: Why Three-Level Calendars Are Ineffective
Ideally, MS Project should allow group-specific scheduling constraints to be factored into mid-level group-specific calendars: e.g.,
    Main: working days run from 8 am until midnight
    Group 1: working days run from 8 am until 5 pm, with a noontime break
    Person 1 has a group 1 schedule, with a vacation during July
    Person 2 has a group 1 schedule, with a vacation during August
    Group 2: working days run from 3 pm until midnight, with a 7 pm break
    Person 3 has a group 2 schedule, with a vacation during September
    Person 4 has a group 2 schedule, with a vacation during October
This architecture would allow each group's calendar – e.g., holidays, working hours – to be adjusted
  in one menu
  independently of all other groups' calendars
Unfortunately, Project only schedules task relative to one base calendar. This effectively prevents the mixing of workers from multiple groups: e.g.,
  if task 1's base calendar is the group 1 calendar, then group 2 will be scheduled according to the group 1 calendar (and similarly for group 2)
  if task 1's base calendar is main, then group 1 and group 2 will be scheduled against main rather than their respective base calendars

## Slide 22: Calendar Architecture and Mid-Level Workgroups
What does work:
    Main: working days run from 8 am until midnight
    Person 1 works from 8-5 with noon lunch and a vacation during July
    Person 2 works from 8-5 with noon lunch and a vacation during August
    Person 3 works from 3-midnight with 7pm break and a vacation during July
    Person 4 works from 3-midnight with 7pm break and a vacation during August
Problem: maintenance overhead created by violating the DRY ("don't repeat yourself") principle of logic design: e.g.,
  To change group 1's workdays from 8-5 to 7-4, person 1 and person 2's work week specifications must both be changed
  To add Bastille Day as a holiday for group 2, person 3 and person 4's work week specifications must both be changed
  What happens when projects are tracking groups of, say, 10-20 employees who are all working different schedules?
I see
  no simple workaround for the need to maintain these calendars in parallel
  no workaround at all, short of writing code to automate the updates

## Slide 23: Project Tracking
Project's Task Information menu is activated by right-clicking on a task, then selecting "Task Information" from the resultant dropdown menu
The menu has a field, Percent complete, which can be set to the percentage of work completed for a given task
  Also, the Task tab's Schedule section has shortcut icons for setting a task's completion percentage to 0%, 25%, 50%, 75%, or 100%
Here, task 1a's and task 1b's percent complete fields have been set to 100% and 50%, respectively.
Note that Project puts a check mark in the ⓘ field for completed tasks.

## Slide 24: Project Tracking
A project's Gantt Chart view indicates completion percentages for individual tasks with red bars. These red bars are embedded in the blue bars that show tasks' scheduled timelines.
Here, task 1a's and task 1b's percent complete fields have been set to 100% and 50%, respectively.
Note that task 1a's and task 1b's embedded bars span all and part of those tasks' blue bars, respectively.
Note that task 2, which hasn't been started, has a totally blue bar

## Slide 25
Other views that indicate project progress include
The Task Usage view, which shows check marks next to completed tasks
The Task Form view, which shows work relative to individual project tasks
The Team Planner view, which shows completed work relative to work resources
The Tracking Gantt view, which shows task bars with percent completion

## Slide 26: Project Tracking
Selecting the Project Tab's Project Information icon accesses a project's Project Information menu.
Selecting this menu's Statistics… control produces a summary statistics table – the same table obtained via the File tab's Project Information dropdown

## Slide 27: Project Tracking
Quite a few of the Task View's columns are concerned with tracking project progress, including
  costs: actual to date, projected, and relative to a baseline cost
  duration: actual to date, projected, and relative to a baseline duration
  start date: actual to date and relative to a baseline start date
  finish date: actual to date, projected, and relative to a baselined finish date
  various metrics for gauging the relationship between baselined and actual progress
These considerations are beyond the scope of this slide deck

## Slide 28: Limitations and Gotchas

## Slide 29: No "True" Support for DRY Task Definition
"DRY" – don't repeat yourself
Problem – lack of subprocedures
  A task that must be done k times must be copied into schedule k times
  This is seriously bad
    Changes to one instance of a task requires changes to all for consistency
    Can't use subprojects as workaround, since subprojects may only be included once
Could in theory be finessed with macros
  This, however, would be clumsy to implement

## Slide 30: No "True" Support for DRY Calendar Definition
Described earlier in slides
  This is also seriously bad – for complex projects
Problem – lack of "calendar inheritance"
  In earlier examples, it should be possible to schedule
    person 1, qualified by the main, group 1, and person 1 calendars applied in succession
  when
    the main calendar is specified as the base calendar for the group 1 and group 2 calendars
    the group 1 calendar is specified as the base calendar for the person 1 and 2 calendars
    the group 2 calendar is specified as the base calendar for the person 3 and 4 calendars
Again, could in theory be finessed with macros
  This, however, would be clumsy to implement

## Slide 31: Limited Support for Summary Statistics
Can't compose queries that retrieve (e.g.)
  average task time
  longest task
  most deeply nested tasks
  all tasks with a custom field with a given value
Can work around this by (e.g.)
  exporting to XML
  using XML query language, XQuery, to generate summary statistics
Hope to show some such queries this fall

## Slide 32: Weak Support for Contingency Planning
From what I can tell, MS Project can't be used to
  specify three-point estimates
    Biafore, "MS Project 2010: Missing Manual", p. 107 shows a schedule with "Best, Probable, and Worst" columns
    These columns, however, are apparently user-managed comment (i.e., text) columns that are ignored for scheduling
  specify that one task should only be triggered if another fails or succeeds
You can, however,
  copy a plan and tinker with the copy (recommended by Biafore)
  inactivate and reactivate tasks
    this would allow for the creation of a worst-case WBS, then the subsequent marking of unneeded tasks as inactive

## Slide 33: Weak Support for Relative Constraints
Can't constrain one task to start or finish within a given time relative to start or finish time for second
  Example: cooler must be loaded into car within an hour of packing it
Best that I've figured out
  Use start-start or finish-finish dependencies
  Use guestimated lead-lag times to adjust start time or end time of dependent task
  Example: start-start dependency between packing cooler, loading car with 15 minute lag on loading (assuming, say, 15 minutes to load cooler)

## Slide 34: Scheduling Intelligence Sometimes an Issue
Slides show schedules where leveling doesn't level task assignments to (e.g.) the nearest hour
I've seen examples where the reverse is true
  "Level all" complains that it can't level some tasks, while
  Incrementally rescheduling these tasks resolves overallocation
One point in Project's favor: scheduling is HARD
  Example of what theoreticians refer to as NP-Complete problem
    "Straightforward" to determine if given schedule is optimal;
    Believed, unfortunately, to be exponentially hard to find it

## Slide 35: Leveling Can Be Slow
I've run leveling jobs that have taken more than an hour to complete
  Leveling large numbers of tasks (> 300) with, say, 12 resources on different work schedules can really tax Project
Recommendations
  Avoid Project's option for automatically leveling tasks after every change to schedule (off by default)
  If possible, manage small changes to large schedules by limiting leveling to affected resources, tasks
    More effective for later in process; less so for early tasks
  Find something else to do when running big leveling jobs
    Accept that scheduling is just difficult
    Be happy that Project is doing it for you

## Slide 36: Project's User Interface Is Sometimes Unstable
I've seen content disappear from views, including
  Gantt timelines from Gantt views
  Task rectangle icons from Team Planner
Fixes
  All views with vertical dividers: check position of divider bar between Task Sheet and Gantt Chart – it moves unexpectedly
  Team Planner View issues: right-click on timeline headers for time frames for which rectangles have disappeared

## Slide 37: Somewhat Unstable Operation
I've seen
  task times set to 48+ million minutes
  task times drop to 0 minutes
  Excel cut-and-paste quit working while using Project to level
  crashes
Big leveling jobs seem to be particularly troublesome
Possible fixes
  revert project to best previous state
    for complex projects, making backup copy before editing can save considerable time
  close, restart
  worst case: reboot Windows

## Slide 38: Assorted Cautions
Task Sheet's Find/Replace controls differ from "normal' MS find/replace features
  must specify a column
  no support for "find/replace" within a selection
  no support for regular-expression-based find/replace
  no support for "find/replace" over rolled up tasks
    entire task hierarchy must be visible in order to do a complete find/replace on a given search string
Project 2010's Undo/Redo controls are global
  undo and redo rewind across multiple sheets