## Slide 1: Microsoft Project 2010 – Introduction, Part 1
Phil Pfeiffer
Fall, 2014

## Slide 2: Project 2010
Purpose: support project definition, scheduling, tracking
Characterized by some as "heavyweight" tool
  Much more fully featured than spreadsheets …
  … but with significant learning curve
My take
  idiosyncratic
  somewhat unstable
  inferior, from what I've heard, to other commercial tools
  useful, even with all of the difficulties
  relatively inexpensive – esp. when compared with these other commercial tools
  a reasonable tool for managing projects

## Slide 3: Characteristics
Project 2010's world model
  A project is a set of partially ordered tasks
  Completed with the help of resources (work, materials, costs)
  Over time
Fundamental feature: Task Sheet
  Hierarchical depiction of a project's tasks, with
    Supporting properties: e.g.,
      Task name
      Start/ end dates
      Resources that task requires (people, equipment, …)
      Predecessor tasks
    Supporting operations: e.g.,
      Linking of projects to subprojects
      Automated scheduling of tasks, a.k.a. leveling
      Automated computation of resource usage and costs

## Slide 4: Selected Supporting Features
Gantt Chart – task sheet, with graph depicting
  tasks in time, with support for expressing and managing
  inter-task dependencies and resource allocations
Resource Sheet – table of resources and characteristics; e.g.,
  cost per hour – standard time and overtime
  working calendar
Resource Usage – breakdown of usage by resource; e.g.,
  summary of usage for project as a whole, in (e.g.) minutes
  breakdown of usage, relative to a time-slot-based view of project time
Team Planner – table-based breakdown of resource usage
Network Diagram – graphical representation of task flow

## Slide 5: This Presentation's Structure
Part 1
  Common features & their uses
    Gantt Chart View
    Tasks
    Scheduling Modes: Manual Mode
    Inter-Task Dependencies
    Resources
    Other Operations on Tasks
Part 2
  Common features, uses (cont.)
    Overallocation
    Duration, Units, Work
    Scheduling Modes: Auto Scheduling
    Scheduling Modes: Recommendations
Part 3
  Common features, uses (cont.)
    Summary tasks and subtasks
    Summary Tasks: Auto Scheduling
    Summary Tasks: Inter-Task Dependencies
    Calendars
    Calendar Management
Part 4
  Common features, uses (cont.)
    Calendar Management (cont.)
    Modifying Calendars
    Skewed Calendars
    Calendar Architectures
    Project Tracking
  Key limitations and gotchas

## Slide 6: Common Features and their Uses

## Slide 7: Project's Primary "Face" - Gantt Chart View
Task Sheet (left) divided by sliding bar (center) from Gantt Chart (right)
Task sheet, Gantt chart initially empty
Image of initial blank project

## Slide 8: Gantt Chart View: Initial, Blank Project
Gantt chart view also includes a timeline view of project schedule
Timeline view, like task sheet and Gantt chart, initially empty

## Slide 9: Gantt Chart View: Initial, Blank Project
Timeline view can be disabled and reenabled using View Tab's Timeline Control

## Slide 10: Gantt Chart View: Initial, Blank Project
Task sheet 's initial mix of properties shown here
Eight of 427 possible task-related fields that Project 2010 supports
These defaults appear to be hard-wired into Project 2010

## Slide 11: Gantt Chart View: Initial, Blank Project
First and final additional task sheet columns
show current row's line number for nonempty rows
support addition of more fields to view

## Slide 12: Gantt Chart View: Initial, Blank Project w. Work
Work column shows a task's total workload
Added to default display by
Selecting down arrow on right-hand side of "Add new column" column
Selecting "work" from alphabetized, pop-up list
Useful for seeing how duration and resource parameters affect schedule

## Slide 13: Gantt Chart View: Initial, Blank Project
Gantt chart's initial time frame and display shown here
Two-level breakdown of time, by day (bottom level) and week (top level), starting with current day
These defaults appear to be hard-wired into Project 2010

## Slide 14: Gantt Chart View: A First, Minimal Task
New task defined by typing task name into Task Name column

## Slide 15: Gantt Chart View: A First, Minimal Task
On task creation, Project
initializes line number field
notes scheduling mode in Task Mode field

## Slide 16: Gantt Chart View: A First, Minimal Task
Line numbers support definition of ordering constraints
Used in predecessor fields to link related tasks
Convenient for tracing sequences of related tasks in a schedule
Project propagates changes to relative task position to predecessors column automatically – like what happens in Excel

## Slide 17: Gantt Chart View: A First, Minimal Task
Task mode field shows mode that Project uses to schedule this task
icon indicates manually scheduled task

## Slide 18: Gantt Chart View: A First, Minimal Task
Scheduling mode assignment for newly created tasks controlled by Task mode control on lower toolbar

## Slide 19: Project Scheduling Modes: Manual Mode
One of two Project 2010 modes for scheduling tasks
  New in Project 2010
  Intended use: building initial list of tasks before estimating them
Default for new projects
Selected characteristics
  Allows users to put any text in time-related fields, including
    No content at all
    Content that Project 2010 can't parse: e.g., "soon", "eventually"
    Content that Project 2010 can parse
      Time points in various formats: e.g., 7/14/14
      Durations in various formats: e.g., 2h, 3 days
  Mode's scheduling logic uses well-formed duration, start, and finish fields to automatically derive dependent fields: e.g.,
    Derive duration from start and finish dates
    Derive start date from duration and finish date
    Derive finish date from duration and start date

## Slide 20: Gantt Chart View: A First, Minimal Task
Scheduling mode assignment for newly created tasks controlled by Task mode control on lower toolbar
Clicking on control produces dropdown, allows toggling between manual scheduling and auto scheduling (more later)

## Slide 21: Gantt Chart View: A First, Minimal Task
Project's Gantt Chart remains empty after sample task was added because task lacks duration, predecessor and successor tasks and resource assignments

## Slide 22: Gantt Chart View: A First, Minimal Task
Similarly, Timeline View remains empty, showing start date equal to finish date (and equal to current date)

## Slide 23: Gantt Chart View: Minimal Task, 2-Day Duration
Adding value to duration field adds blue bar to Gantt Chart
Gantt chart now shows task's duration, using blue bar
Task bar lacks start interval ([) and end interval (]) icons that are present for tasks with explicitly defined start and finish dates.

## Slide 24: Gantt Chart View: Minimal Task, 2-Day Duration
In absence of well-formed content in Start field, MS Project uses current Project's start date to schedule task 1
Start date viewable, settable from Project Information menu
  Tab accessible from Project tab's Project Information option
Defaults to day when .mpp file was created

## Slide 25: Gantt Chart View: Minimal Task, 2-Day Duration
Adding value to duration field also updates timeline's start, finish times.

## Slide 26: Gantt Chart View: Minimal Task, 7/14 Start
Setting start date of 7/14 with no supporting content inserts start interval icon ([) – and no more – into Gantt Chart

## Slide 27: Gantt Chart View: Minimal Task, 7/15 Finish
Setting finish date of 7/15 with no supporting content inserts end interval icon (]) – and no more – into Gantt Chart

## Slide 28: Gantt Chart View: Start, Duration, Finish
If any two of {start date, duration, finish date} is set, Project infers the third value and generates the Gantt chart task bar: i.e.,
start interval icon ([)
blue duration bar
end interval icon (])
Here, I specified start and finish dates and allowed Project to infer duration.

## Slide 29: Gantt Chart View: Modifying Timescales
Right-clicking on Gantt chart timescale bar produces pop-up window
Selecting "timescale…" then raises a timescale menu

## Slide 30: Gantt Chart View: Modifying Timescales
Timescale menu options support changes to task attributes, including
Tier to vary (via tabs: default is Middle Tier)
Time in units for this tier (via units and count fields)
Number of tiers (default is 2; can be 1 or 3)

## Slide 31: Gantt Chart View: Modifying Timescales
Timescale menu can also be accessed as last item on dropdown menu accessible from View Tab's Timescale option

## Slide 32: Gantt Chart View: Modifying Timescales
Showing effect of adjusting Gantt chart timescales with
middle tier = 1 day
bottom tier = 8 hours

## Slide 33: Gantt Chart View: 2 Independent Tasks
Adding second task to schedule with no specified start date schedules task for earliest available start time. Lack of other constraints allows for overlap.

## Slide 34: Gantt Chart View: 2 Tasks, FS Dependency
Making sample task 1 a predecessor of sample task 2 yields a three-day schedule.
The Gantt chart uses a small arrow to show inter-task dependency, with arrow pointing towards the dependent task.
Here, task 2 is said to have a finish-to-start (FS) dependency on task 1.

## Slide 35: Gantt Chart View: 2 Tasks, FS Dependency
Closeup of Gantt Chart depiction of finish-to-start (FS) dependency from previous slide's schedule.

## Slide 36: Gantt Chart View: 2 Tasks, FS Dependency
Right-clicking on task 2 raises task 2's Task Information Menu.
This menu's Predecessors tab shows the dependency from task 1 to task 2 and confirms it as an FS dependency.
The FS designation means that task 2 must wait on task 1 to start, subject to a lag/ lead time.

## Slide 37: 2 Tasks, FS Dependency, 0.5 Day Lag
Lag time is a delay between a first event and a second event that the first triggers.
In Project, lag time is specified using
the task information window OR
by following a predecessor constraint with a "+" and a duration.
The dependency type suffix, FS, can ordinarily be omitted for FS dependencies. It must, however, be shown when specifying a lag.

## Slide 38: 2 Tasks, FS Dependency, 0.5 Day Lag
Adding the 0.5 day lag time to the task 1-task 2 dependency has the effect of pushing task 2's end time from
the end of the 7/16 work day to
four hours into the work day on 7/17—i.e., 12 noon

## Slide 39: 2 Tasks, FS Dependency, 0.5 Day Lead
Lead (pronounced "leed') time is a "head start" given to a second event that a first event triggers.
In Project, lead time is specified as negative lag time.

## Slide 40: 2 Tasks, FS Dependency, 0.5 Day Lead
Adding the 0.5 day lead time to the task 1-task 2 dependency has the effect of changing task 2's end time from
the end of the 7/16 work day to
four hours before the end of the work day on 7/16—i.e., 12 noon

## Slide 41: The Four Types of Inter-Task Dependencies
Finish-to-Start (FS)
  End of one task initiates start of another.
  Example: when summer ends, students start classes.
  By far, the most common type of inter-task dependency.
Start-to-Start (SS)
  Start of one task or event initiates start of another.
  Example: when semester starts, students start classes.
Start-to-Finish (SF)
  Start of one task or event forces end of another.
  Example: start of semester puts an end to "normal" life.
  By far, the least common type of inter-task dependency
Finish-to-Finish (FF)
  End of one task forces end of another.
  Example: end of period puts an end to today's lecture.

## Slide 42: SS, SF, and FF Dependencies

## Slide 43: Resources
An entity that's required to complete a project's task(s)
Project recognizes three types:
  work
    selected by default when a resource is declared
  cost
  materials

## Slide 44: Viewing a Project's Resources
Resource Sheet View
shows a project's resources and their properties
accessed by
  selecting Task tab's Gantt Chart dropdown, then
  selecting Resource Sheet from the resulting menu
initial, blank project has no assigned resources

## Slide 45: Viewing Resource Usage
Summarized in Resource Usage View
shows a project's resources and uses over a project's lifetime, on a per-resource, per-task basis
first section devoted to resource-less tasks, if any in schedule
accessed by
  selecting Task tab's Gantt Chart dropdown, then
  selecting Resource Sheet from the resulting menu

## Slide 46: Declaring Resources
Resources can be added to a project by
  entering them into the resource sheet OR
  naming them into the task sheet's "resource" column (shown here)
Effects of associating task with resource:
  update task's work obligation, if duration, start, and finish known
    by default, Project associates 100% of resource's time to task
    here, 2 day duration * 8 hr default workday = 16 hrs work
  place resource name on Gantt chart, next to task's task bar

## Slide 47: Resource Sheet, Resource Usage Views After Adding Person 1
Top line for each resource shows total usage for resource.
Sample task 2 remains unassigned.

## Slide 48: Team Planner View After Adding Person 1
Team Planner view shows tasks by resource over time.
Hovering the mouse over a task rectangle yields a pop-up window that summarizes that task's key characteristics.
View is accessed via the Task tab's View option, via a dropdown menu.

## Slide 49: Other Operations on Tasks
Cutting, copying, pasting, and deleting tasks
  Operations available through pop-up dropdown menu accessed by right-clicking on task
    Options also available via keyboard shortcut keys (^X, ^C, ^V, delete)
  Possible to cut, copy, paste, and delete groups of tasks
    Pasting groups of cut or copied tasks preserves dependencies within the group
Reordering a project's tasks
  Select a task or (or group of tasks) to move
  Drag the selection to the new spot in the task list
  Note: If the reordering would create a circular dependency (more later), Project will disallow it. If you wish to do a move in this scenario, you will need to break the potential circularity before doing the move.